## User Stories
Story ID | Sprint | Role | Story Title | Story Description | Priority | Story Points | Status
US-001 | Sprint 1 | Owner | Owner Login | As an Owner, I want to login to the admin panel so that I can access the gym management features | High | 5 | Todo
US-002 | Sprint 1 | Owner | View Dashboard | As an Owner, I want to see a dashboard with key metrics so that I can quickly assess gym performance | High | 8 | Todo
US-003 | Sprint 1 | Owner | Create Staff Account | As an Owner, I want to create staff accounts so that front desk staff can use the system | High | 5 | Todo
US-004 | Sprint 2 | Staff | Search Members | As a Staff, I want to search for members by name/phone so that I can quickly find member details | High | 3 | Todo
US-005 | Sprint 2 | Staff | Create New Member | As a Staff, I want to create a new member with basic info so that new customers can be registered | High | 5 | Todo
US-006 | Sprint 2 | Staff | View Member Profile | As a Staff, I want to view a member's profile so that I know if they can access the gym | High | 3 | Todo
US-007 | Sprint 3 | Owner | Create Membership Plan | As an Owner, I want to create membership plans so that I can define pricing tiers | High | 5 | Todo
US-008 | Sprint 3 | Staff | Assign Membership | As a Staff, I want to assign a membership plan to a member so that their gym access is activated | High | 5 | Todo
US-009 | Sprint 3 | System | Auto Update Membership Status | As a System, I want membership status to automatically change to EXPIRED when end_date passes | High | 8 | Todo
US-010 | Sprint 4 | Staff | Check-in Member | As a Staff, I want to perform check-in for a member so that attendance is tracked | High | 5 | Todo
US-011 | Sprint 4 | Staff | Validate Membership on Check-in | As a Staff, I want to be prevented from checking in expired members so that only valid members access | High | 3 | Todo
US-012 | Sprint 4 | Owner | View Today's Check-ins | As an Owner, I want to see today's check-ins list so that I can monitor attendance | Medium | 3 | Todo
US-013 | Sprint 2 | Staff | Edit Member Info | As a Staff, I want to edit member information so that member data stays up to date | Medium | 3 | Todo
US-014 | Sprint 3 | Staff | View Membership History | As a Staff, I want to view a member's membership history so that I can see past memberships | Medium | 3 | Todo
US-015 | Sprint 4 | Owner | View Check-in Reports | As an Owner, I want to view check-in reports so that I can analyze attendance trends | Medium | 8 | Todo

## Tasks
Task ID | Story ID | Module | Task Description | Tech Stack | Status
T-001 | US-001 | Authentication | Setup Laravel Breeze authentication | Laravel Breeze | Todo
T-002 | US-001 | Authentication | Create login blade template | Blade, Tailwind | Todo
T-003 | US-001 | Authentication | Setup role-based access control | Laravel Gates/Policies | Todo
T-004 | US-002 | Dashboard | Create dashboard controller | Laravel Controller | Todo
T-005 | US-002 | Dashboard | Design dashboard layout with cards | Blade, Tailwind | Todo
T-006 | US-002 | Dashboard | Write SQL queries for metrics | Laravel Eloquent | Todo
T-007 | US-003 | Staff Management | Create staff creation form | Blade, Tailwind | Todo
T-008 | US-003 | Staff Management | Implement staff controller (create/store) | Laravel Controller | Todo
T-009 | US-004 | Member Search | Create search form UI | Blade, Alpine.js | Todo
T-010 | US-004 | Member Search | Implement member search controller | Laravel Controller | Todo
T-011 | US-005 | Member Management | Create member form template | Blade, Tailwind | Todo
T-012 | US-005 | Member Management | Implement member creation controller + auto generate member_id | Laravel Controller | Todo
T-013 | US-005 | Member Management | Add validation for member data | Laravel Form Request | Todo
T-014 | US-006 | Member Profile | Create member profile page | Blade, Tailwind | Todo
T-015 | US-006 | Member Profile | Display membership status on profile | Blade, Eloquent | Todo
T-016 | US-007 | Membership Plans | Create membership plan form | Blade, Tailwind | Todo
T-017 | US-007 | Membership Plans | Implement membership plan CRUD | Laravel Controller | Todo
T-018 | US-008 | Membership Assignment | Create membership assignment form | Blade, Tailwind | Todo
T-019 | US-008 | Membership Assignment | Implement membership logic (start_date, end_date, status) | Laravel Model, Controller | Todo
T-020 | US-009 | Membership Status | Create database migration for memberships | Laravel Migration | Todo
T-021 | US-009 | Membership Status | Setup schedule/job for daily membership status update | Laravel Scheduler | Todo
T-022 | US-010 | Check-in | Create check-in form UI | Blade, Tailwind | Todo
T-023 | US-010 | Check-in | Implement check-in controller | Laravel Controller | Todo
T-024 | US-011 | Check-in Validation | Add membership validation logic before check-in | Laravel Service | Todo
T-025 | US-012 | Check-in Reports | Create today's check-ins list page | Blade, Tailwind | Todo
T-026 | US-012 | Check-in Reports | Implement check-in query and display | Laravel Eloquent | Todo
T-027 | US-013 | Member Edit | Create member edit form | Blade, Tailwind | Todo
T-028 | US-013 | Member Edit | Implement member update controller | Laravel Controller | Todo
T-029 | US-014 | Membership History | Create membership history view | Blade, Tailwind | Todo
T-030 | US-015 | Reports | Create check-in reports page | Blade, Tailwind | Todo

## Acceptance Criteria
Story ID | Criteria # | Acceptance Criteria
US-001 | 1 | Owner can input email and password
US-001 | 2 | System validates email and password
US-001 | 3 | Owner is redirected to dashboard on successful login
US-001 | 4 | Error message shows on failed login
US-002 | 1 | Dashboard displays total count of active members
US-002 | 2 | Dashboard displays count of today's check-ins
US-002 | 3 | Dashboard displays total revenue for current month
US-002 | 4 | All metrics update in real-time or refresh on page load
US-003 | 1 | Owner can input staff name, email, and password
US-003 | 2 | System generates unique account for staff
US-003 | 3 | Staff receives login credentials
US-003 | 4 | Staff is assigned 'STAFF' role automatically
US-004 | 1 | Staff can search by member name (partial match)
US-004 | 2 | Staff can search by member phone number
US-004 | 3 | Search results display member ID, name, phone, status
US-004 | 4 | Staff can click result to view full member profile
US-005 | 1 | Form requires name, phone, gender, date of birth
US-005 | 2 | Phone number is validated as unique
US-005 | 3 | System auto-generates unique member_id (e.g., GYM001)
US-005 | 4 | New member is created with status ACTIVE
US-006 | 1 | Member profile displays all personal information
US-006 | 2 | Profile shows current membership (plan, start_date, end_date, status)
US-006 | 3 | Profile shows button to extend/assign membership
US-006 | 4 | Profile shows check-in history for last 30 days
US-007 | 1 | Owner can input plan name, duration (days), and price
US-007 | 2 | Owner can set plan as active/inactive
US-007 | 3 | All plans are displayed in a list with edit/delete options
US-007 | 4 | Inactive plans cannot be assigned to new members
US-008 | 1 | Staff selects member and membership plan from dropdowns
US-008 | 2 | System auto-calculates end_date = start_date + plan duration
US-008 | 3 | Membership status is set to ACTIVE
US-008 | 4 | Member can now check-in to gym
US-009 | 1 | Daily job runs to check expired memberships
US-009 | 2 | Memberships with end_date < today are marked EXPIRED
US-009 | 3 | Check-in is blocked for EXPIRED memberships
US-009 | 4 | Owner can see membership expiry notifications
US-010 | 1 | Staff enters member ID or searches by name/phone
US-010 | 2 | System displays member name and current membership status
US-010 | 3 | Clicking 'Check-in' logs timestamp and saves check-in record
US-010 | 4 | Success message displays after check-in
US-011 | 1 | Check-in form checks if member membership status = ACTIVE
US-011 | 2 | If expired, error message 'Membership expired - please renew'
US-011 | 3 | Check-in button is disabled for expired members
US-011 | 4 | Quick link to renew membership appears for expired members
US-012 | 1 | Page displays all check-ins from today
US-012 | 2 | List shows member name, time checked-in, checked-in by (staff name)
US-012 | 3 | Owner can filter/search in today's list
US-012 | 4 | List refreshes or can be manually refreshed
US-013 | 1 | Edit form pre-populates with current member data
US-013 | 2 | Staff can update name, phone, email, gender
US-013 | 3 | Updated data is saved to database
US-013 | 4 | Success message confirms update
US-014 | 1 | Member profile tab shows 'Membership History'
US-014 | 2 | History lists all past and current memberships with plan, dates, status
US-014 | 3 | Latest membership appears at the top
US-014 | 4 | History is sortable by date
US-015 | 1 | Owner can select date range for report
US-015 | 2 | Report shows daily check-in count
US-015 | 3 | Report shows weekly/monthly summary
US-015 | 4 | Report can be exported as PDF or CSV

## Sprint Planning
Sprint | Start Date | End Date | Stories | Total Story Points | Team Capacity | Status
Sprint 1 | 2026-01-13 | 2026-01-27 | US-001, US-002, US-003 | 18 | 20 | Not Started
Sprint 2 | 2026-01-30 | 2026-02-13 | US-004, US-005, US-006, US-013 | 14 | 20 | Not Started
Sprint 3 | 2026-02-16 | 2026-03-02 | US-007, US-008, US-009, US-014 | 21 | 20 | Not Started
Sprint 4 | 2026-03-05 | 2026-03-19 | US-010, US-011, US-012, US-015 | 19 | 20 | Not Started

## Data Dictionary
Table Name | Column Name | Data Type | Nullable | Description
users | id | INT (PK) | NO | Unique user identifier
users | name | VARCHAR(255) | NO | User full name
users | email | VARCHAR(255) | NO | User email (unique)
users | password | VARCHAR(255) | NO | Hashed password
users | gym_id | INT (FK) | NO | Reference to gyms table
users | role | ENUM | NO | User role (OWNER/STAFF)
users | created_at | TIMESTAMP | NO | Account creation time
members | id | INT (PK) | NO | Unique member identifier
members | gym_id | INT (FK) | NO | Reference to gyms table
members | member_id | VARCHAR(50) | NO | Unique member code (GYM001)
members | full_name | VARCHAR(255) | NO | Member full name
members | phone | VARCHAR(20) | NO | Member phone (unique)
members | email | VARCHAR(255) | YES | Member email (unique)
members | gender | ENUM | YES | Member gender (M/F/OTHER)
members | date_of_birth | DATE | YES | Member date of birth
members | status | ENUM | NO | Member status (ACTIVE/INACTIVE)
members | created_at | TIMESTAMP | NO | Record creation time
membership_plans | id | INT (PK) | NO | Unique plan identifier
membership_plans | gym_id | INT (FK) | NO | Reference to gyms table
membership_plans | name | VARCHAR(255) | NO | Plan name (Bulanan, 3 Bulan)
membership_plans | duration_days | INT | NO | Plan duration in days
membership_plans | price | DECIMAL(10,2) | NO | Plan price
membership_plans | is_active | BOOLEAN | NO | Plan active status
memberships | id | INT (PK) | NO | Unique membership identifier
memberships | member_id | INT (FK) | NO | Reference to members table
memberships | membership_plan_id | INT (FK) | NO | Reference to membership_plans table
memberships | start_date | DATE | NO | Membership activation date
memberships | end_date | DATE | NO | Membership expiration date
memberships | status | ENUM | NO | Status (ACTIVE/EXPIRED/FROZEN)
memberships | auto_renew | BOOLEAN | NO | Auto renew flag
checkins | id | INT (PK) | NO | Unique check-in identifier
checkins | member_id | INT (FK) | NO | Reference to members table
checkins | gym_id | INT (FK) | NO | Reference to gyms table
checkins | checked_in_at | TIMESTAMP | NO | Check-in timestamp
checkins | checked_in_by | VARCHAR(255) | YES | Staff name who checked-in
payments | id | INT (PK) | NO | Unique payment identifier
payments | gym_id | INT (FK) | NO | Reference to gyms table
payments | member_id | INT (FK) | NO | Reference to members table
payments | amount | DECIMAL(10,2) | NO | Payment amount
payments | payment_for | VARCHAR(50) | NO | Payment type (membership/class)
payments | method | ENUM | NO | Payment method (CASH/TRANSFER/CARD)
payments | status | ENUM | NO | Payment status (PAID/PENDING)